## Team Tracker
Task Name | Task Description | Assigned To | Priority | Documents | Status | Start Date | Due Date | Comments
ML Model |  | Mostafa | Urgent | provided | Completed |  | 2025-11-04 | Mostafa is not accepting any tasks. The model will be revamped.
Database + PowerBI + Visualization |  | Mohamed Alaa Mohamed Fekry | High |  | In progress | 14/4/2025 | 22/4/2025
Report consolidation and preparations |  | Mohamed Fekry | Low |  | In progress | 13/4/2025
ML Model |  | Hassan waked | Urgent++ |  | Not started | 14/4/2025 | 15/4/2025 | Sick
Revamp the process + Deployment |  | Mohamed Moselhy | High |  | In progress | 2025-12-04 | 25/4/2025 | Started from scratch

## Load
Assigned To | Free time to work in project | Task
Mostafa | --------
Mohamed Alaa | Not provided | Database + PowerBI
Mohamed Fekry | Not provided | Consultation, Reports
Hassan waked | Not provided | Model
Mohamed Moselhy